## Sheet1
DE CAKE WORLD
Identified By: Amrutha Raj
Reported to:
Date:31/03/2023
Version No:
Environmental Details:
Bug ID | Expected Result | Bug Description | Steps to Reproduce | Severity | Priority | Screenshot | Status
DEF_DCW_01 | All fields under Our Menu Card option should work | Fields under Our Menu Card option is not working | 1.locate our menu card option 2.click on our menu card option 3.click on each fields under our menu card option | Critical |  | https://drive.google.com/file/d/1zdywM3vJYuV_1hm4Z3xzMxiuNQ1z5MHz/view?usp=share_link | New
DEF_DCW_02 | All fields under Our Menu Card option should navigate to the next page and show the details | fields under Our Menu Card option is navigating to next page and showing category not found | 1.click on each field under our menu card option | Critical |  | https://drive.google.com/file/d/1dI9VDkZdYwljEd2ZT53KC0GJvU23QKs1/view?usp=share_link | New
DEF_DCW_03 | should show the price details of cakes | Not showing the price details of cakes | 1.locate the image of cake 2.click on the option cake 1 | Critical |  | https://drive.google.com/file/d/1gLOZcFGyHLvRY_fjsBAXX5MNFsEe-f7n/view?usp=share_link | New
DEF_DCW_04 | Additional info field should work | additional info field is not working | 1.locate additional info field 2.click on the dropdown list | critical |  | https://drive.google.com/file/d/1gLOZcFGyHLvRY_fjsBAXX5MNFsEe-f7n/view?usp=share_link | New
DEF_DCW_05 | Text to display field should work | text to display field is not working | 1.locate text to display field 2.click on the dropdown list | Critical |  | https://drive.google.com/file/d/1wNQXDCVGlcULT4QhZj5iotJCzrh2p94p/view?usp=share_link | New
DEF_DCW_06 | Add to cart option should work | Add to car option is not working | 1.locate add to cart option 2.click on add to cart option | Critical |  | https://drive.google.com/file/d/1UBK7-ocrCTiZzK83yug4VWCEHlMtMCSF/view?usp=share_link | New
DEF_DCW_07 | Compare this product option should work | compare this product option is not working | 1.locate compare this product option 2.click on compare this product | critical |  | https://drive.google.com/file/d/1unvG_hSyUZ5pIC9Mt9DIuWiDnQlkkH79/view?usp=share_link | New
DEF_DCW_08 | When clicking on Vimeo option should navigate to Vimeo page | When clicking on Vimeo logo not navigating to Vimeo page | 1. locate Vimeo logo 2.click on Vimeo logo | Trivial |  | https://drive.google.com/file/d/13KYvYISCH6r76_7YJKbsJw0LO5tjkCBg/view?usp=share_link | New
DEF_DCW_09 | When clicking on facebook option should navigate to facebook page | When clicking on facebook logo not navigating to facebook page | 1.locate facebook logo 2. click on facebook logo | Trivial |  | https://drive.google.com/file/d/13KYvYISCH6r76_7YJKbsJw0LO5tjkCBg/view?usp=share_link | New
DEF_DCW_10 | When clicking on youtube option should navigate to youtube page | When clicking on youtube logo not navigating to youtube page | 1.locate youtube logo 2. click on youtube logo | Trivial |  | https://drive.google.com/file/d/13KYvYISCH6r76_7YJKbsJw0LO5tjkCBg/view?usp=share_link | New
DEF_DCW_11 | When clicking on LinkedIn Logo should navigate to LinkedIn page | When clicking on LinkedIn logo not navigating to LinkedIn page | 1.locate linkedin logo 2.click on LinkedIn logo | Trivial |  | https://drive.google.com/file/d/13KYvYISCH6r76_7YJKbsJw0LO5tjkCBg/view?usp=share_link | New
DEF_DCW_12 | When clicking on Twitter Logo should navigate to Twitter page | When clicking on Twitter logo not navigating to Twitter page | 1.locate twitter logo 2.click on Twitter logo | Trivial |  | https://drive.google.com/file/d/13KYvYISCH6r76_7YJKbsJw0LO5tjkCBg/view?usp=share_link | New
DEF_DCW_13 | When clicking on Google Logo should navigate to google page | When clicking on google logo navigating to error page | 1.locate google logo 2.click on google logo | Trivial |  | https://drive.google.com/file/d/1iLbYHYYb-7rSUqUv2N-rEqcbvNXYmOuG/view?usp=share_link | New
DEF_DCW_14 | The size guide option should provide dimension of cake | the size guide option is prividing the dimensions of cloths | 1.locate size guide option 2.click on size guide option | Trivial |  | https://drive.google.com/file/d/16Fd0zbtZUuSgOxLlz7EE5dHk4_IxlFRQ/view?usp=share_link | New
DEF_DCW_15 | shipping option should provide details of cake shipping | shipping option is providing details of clothing | 1.locate shipping option 2.click on shipping option | Trivial |  | https://drive.google.com/file/d/1RFa4TbzJV0N9uZstYjR4lI1XP4FpQ9ZT/view?usp=share_link | New
DEF_DCW_16 | Category option should work | category option is not working | 1.Locate Category option 2.click on category | Critical |  | https://drive.google.com/file/d/1fJR8ApYtPaHoTJlBJpNDiNEkfrMw19p_/view?usp=share_link | New
DEF_DCW_17 | About us option should work | About us option is not working | 1.locate about us option 2.click on about us | Critical |  | https://drive.google.com/file/d/11UQ_JeGaeOU8hATO1KqON6XdTY9MKxY9/view?usp=share_link | New
DEF_DCW_18 | Gallery option should work | gallery option is not working | 1.locate gallery option 2.click on gallery option | Critical |  | https://drive.google.com/file/d/1yCoBZEZG2uq-AkUpTARYzMOziJiLYhAi/view?usp=share_link | New
DEF_DCW_19 | contact us option should contain valid email id,phone number,skype id | contact us option is not providing valid email id,skype id, phone number | 1.locate contact us 2.click on contact us 3.locate email id 4.locate phone mu,ber 5.locate skype id | Trivial |  | https://drive.google.com/file/d/1WkNJD-PI6FVCAINW1kZuBHNQc6IEnb8b/view?usp=share_link | New
DEF_DCW_20 | the provided map should be exact location of De cake world shop | the provided map is not showing the location of De cake world shop | 1.locate the map 2.check the map | Trivial |  | https://drive.google.com/file/d/1x6M_IIS_MNiJVw-eSWZV1FpoZyUfaoYe/view?usp=share_link | New
DEF_CW_21 | when clicking on all the provided payment option logo should navigate to next page | when clicking on all the provided payment option logo is not navigating to next page | 1.locate all the payment logo 2.click on all the payment logo | Critical |  | https://drive.google.com/file/d/11pFlAqwyrgVr_Gi_mIFxH2M7QFZ2D__c/view?usp=share_link
DEF_CW_22 | Send message option should work | Send message option is not working | 1.locate send message 2.click on send message | Trivial |  | https://drive.google.com/file/d/11pFlAqwyrgVr_Gi_mIFxH2M7QFZ2D__c/view?usp=share_link
DEF_CW_23 | Live Chat option should work | Live Chat option is not working | 1.locate Live Chat 2.click on LiveChat | Trivial |  | https://drive.google.com/file/d/11pFlAqwyrgVr_Gi_mIFxH2M7QFZ2D__c/view?usp=share_link

## Sheet2
DE CAKE WORLD
Tested By:Amrutha Raj |  |  |  | Date:7/05/2023
Environment Details: Browser and OS |  |  |  | Module:
Test ID | Test Description | Test Procedure | Test Data | Expected Result | Actual Result | Status
DCW_HP_01 | Ensure the De Cake World shop logo is present | 1.Open De Cake World website 2.Locate the logo | http://www.decakeworld.com/ | Logo should be present | Logo is present | pass
DCW_HP_02 | Ensure all fields are clearly visible | 1. Locate all fields |  | All fields should be clearly visible | All fields are clearly visible | pass
DCW_HP_03 | Check whether all fields in home page are clickable or not | 1.Click on each fields |  | All fields in home page should be clickabe | All fields in home page is clickabe | pass
DCW_HP_04 | Check whether the available options are showing when clicking on Our Menu Card option | 1.Locate Our Menu Card option 2.Click on Our Menu Card option |  | When clicking on Our Menu Card option should show the available options | Available options is present when clicking on Our Menu Card option | Pass
DCW_HP_05 | Ensure all the fields under Our Menu Card option is clickable or not | 1.Click on Our Menu Card option 2.Click on each fields under Our Menu Card option |  | All the fields under Our Menu Card option should be clickable | All the fields under Our Menu Card option is clickable | pass
DCW_HP_06 | Check whether all the fields under Our Menu Card option is navigating to next page | 1. Locate Our Menu Card option 2.Click on each field under Our Menu Card option |  | clicking on all the fields under Our Menu Card option should navigate to next page | all the fields under Our Menu Card option is navigating to next page | pass
DCW_HP_07 | Check whether the navigated page of Our Menu Card option should shows proper details | 1. Click each field under Our Menu Card option |  | The navigated page should show proper details | The navigated page is not showing proper details | fail
DCW_HP_08 | Check whether the category names are showing when clicking on Categories option | 1.Locate Category option 2.Click on Category option |  | when clicking on Categories option category names should be show | when clicking on Categories option category names | pass
DCW_HP_09 | Check whether all the fields under Category option is navigating to next page | 1.Click on Category option 2.click on each field under Category option |  | when clicking on all the fields under Category option should navigate to next page | clicking on all the fields under Category option is navigating to next page | pass
DCW_HP_10 | Check whether the navigated page of Category option should shows proper details | 1. Click on each field |  | The navigated page should show proper details | The navigated page is not showing proper details | fail
DCW_HP_11 | Check whether the About Us option is navigate to next page | 1. Locate About Us option 2.click on About Us option |  | when clicking on About Us option should navigate to next page | clicking on About Us option is navigating to next page | pass
DCW_HP_12 | Check whether the navigated page of About Us option should shows proper details | 1.click on About Us option |  | The navigated page should show proper details | The navigated page is not showing proper details | fail
DCW_HP_13 | Check whether Gallery option is navigating to next page | 1. Locate Gallery option 2.click on Gallery option |  | When clicking on Gallery option should navigate to next page | When clicking on Gallery option should navigate to next page | pass
DCW_HP_14 | Check whether the navigated page of Gallery option is showing proper details | 1.click on Gallery option |  | The navigated page should show proper details | The navigated page is not showing proper details | fail
DCW_HP_15 | Check whether all the fields under Category option is navigating to next page | 1. Locate information on side of Mobile No edit text field |  | When clicking on Gallery option should navigate to next page | When clicking on Gallery option should navigate to next page | pass
DCW_HP_16 | Check whether all the fields under Contact option is navigating to next page | 1. Locate Contact option 2.Click on Contact option |  | When clicking on Contact option should navigate to next page | When clicking on Contact option should navigate to next page | pass
DCW_HP_17 | check whether contact us option contains valid email id,phone number,skype id | 1. click on Contact option |  | Contact us option should contain valid email id,phone number,skype id | Contact us option not contains valid email id,phone number,skype id | fail
DCW_HP_18 | Ensure that the provided map is the exact location of De cake world shop | 1. locate map 2.check map |  | the provided map should be the exact location of De cake world shop | the provided map is not showing the exact location of De cake world shop | Fail
DCW_HP_19 | check whether the provided payment option is navigating to next page when clicking on the logos | 1.locate the logos 2.click on logos |  | the provided payment option should navigate to next page when clicking on the logos | the provided payment option is not navigating to next page when clicking on the logos | fail
DCW_HP_20 | check whether the Add to cart option is working or not | 1. Locate Add to cart option 2.click on add to cart option |  | Add to cart option should work | Add to cart option is not working | fail
DCW_HP_21 | check whether When clicking on Vimeo logo is navigating to Vimeo page | 1.locate vimeo logo 2.click on vimeo logo |  | When clicking on Vimeo logo should navigate to Vimeo page | When clicking on Vimeo logo is not navigating to Vimeo page | fail
DCW_HP_22 | check whether When clicking on facebook logo is navigating to facebook page | 1.locate facebook logo 2.click on facebook logo |  | When clicking on facebook logo should navigate to facebook page | When clicking on facebook logo is not navigating to facebook page | fail
DCW_HP_23 | check whether When clicking on twitter logo is navigating to twitter page | 1.locate twitter logo 2.click on twitter logo |  | When clicking on twitter logo should navigate to twitter page | When clicking on twitter logo is not navigating to twitter page | fail
DCW_HP_24 | check whether When clicking on LinkedIn option is navigating to LinkedIn page | 1.locate LinkedIn logo 2.click on LinkedIn logo |  | When clicking on LinkedIn logo should navigate to LinkedIn page | When clicking on LinkedIn logo is not navigating to LinkedIn page | fail
DCW_HP_25 | check whether When clicking on youtube logo is navigating to youtube page | 1.locate youtube logo 2.click on youtube logo |  | When clicking on youtube logo should navigate to youtube page | When clicking on youtube logo is not navigating to youtube page | fail
DCW_HP_26 | check whether When clicking on Google logo is navigating to Google page | 1.locate Google logo 2.click on Google logo |  | When clicking on Google logo should navigate to Google page | When clicking on Google logo is not navigating to Google page | fail
DCW_HP_27 | check whether the Search option is working or not | 1. Locate Search option 2.click on Search option |  | Search option should work | Search option is working | pass
DCW_HP_28 | check whether the user can enter text in edit text field in the Search option | 1.click on search option 2. enter text | Cakes | the user should able to enter text in edit text field in the Search option | the user can enter text in edit text field in the Search option | pass
DCW_HP_29 | check whether the results is showing or not when user entered text in edit text field in the Search option | 1.click on search option 2. enter text |  | the results should show when user entered text in edit text field in the Search option | the results is show ing when user entered text in edit text field in the Search option | pass
DCW_HP_30 | check whether the Create Account option is working or not | 1. locate Create Account option 2.click on create account option |  | Create Account option should work | Create Account option is working | pass
DCW_HP_31 | check whether all the fields under Create Account option is working or not | 1. locate Create Account option 2.click on create account option 3.click on each field 4.enter email id 5.enter password | amrutha23@gmail.com dfer@124556 | all the fields under Create Account option should work | all the fields under Create Account option is working | pass
DCW_HP_32 | check whether Wishlist option is working or not | 1.locate wishlist option 2.click on wishlist option |  | Wishlist option should work | Wishlist option is not working | fail
DCW_HP_33 | check whether Add to Cart option is working or not | 1.locate Add to Cart option 2.click on Add to Cart option |  | Add to Cart option should work | Add to Cart option is not working | fail
DCW_HP_34 | check whether the images provided are clearly visible or not | 1.locate all the images |  | Images provided should be clearly visible | Images provided are clearly visible | pass
DCW_HP_35 | check whether the Shop Now option is present or not | 1.locate shop now option |  | Shop Now option should present | Shop Now option is present | pass
DCW_HP_36 | check whether the contact number with country code is present or not | 1.Locate contact number |  | contact number with country code should be present | contact number with country code is present | pass
DCW_HP_37 | ensure all the text provided is correct or not | 1.locate all the texts 2.check spelling |  | All the provided text should be correct | All the provided text is correct | pass
DCW_HP_38 | check whether the page is returning to home page when clicking on Home option | 1. locate home option 2.click on home option |  | the page should be return to home page when clicking on Home option | the page is returning to home page when clicking on Home option | pass
DCW_HP_39 | check whether the keyboard shortcuts in map is working or not | 1.locate keyboard shortcuts 2.click on keyboard shortcuts |  | keyboard shortcuts in map should work | keyboard shortcuts in map is working | pass
DCW_HP_40 | check whether the terms of use in map is working or not | 1.locate terms of use 2.click on terms of use |  | terms of use option in map should work | terms of use option in map is working | pass
DCW_HP_41 | check whether the report a map error in map is working or not | 1.locate report a map error 2.click on report a map error |  | report a map error option in map should work | report a map error option in map is working | pass
DCW_HP_42 | check whether the zoom in and zoom out option in map is working or not | 1.locate zoom in and zoom out option 2.click on zoom in and zoom out option |  | zoom in and zoom out option in map should work | zoom in and zoom out option in map is working | pass
DCW_HP_43 | check whether the Show Satellite Imagery option in map is working or not | 1.locate Show Satellite Imagery option 2.click on Show Satellite Imagery option |  | Show Satellite Imagery option in map should work | Show Satellite Imagery option in map is working | pass
DCW_HP_44 | check whether the Show View Larger Map option in map is working or not | 1.locate View Larger Map option 2.click on View Larger Map option |  | Show View Larger Map option in map should work | Show View Larger Map option in map is working | pass
DCW_HP_45 | check whether the Directions option in map is working or not | 1.locate Direction option 2.click on Direction option |  | Direction option in map should work | Direction option in map is working | pass
DCW_HP_46 | check whether the edit text fields in Account Login page is clearly visible | 1.click on Account Login 2.locate all the edit text fields |  | the edit text fields in Account Login page should be clearly visible | the edit text fields in Account Login page is clearly visible | pass
DCW_HP_47 | check whether the edit text fields in Account Login page is clickable or not | 1.click on Account Login 2.locate all the edit text fields 3.click on each field |  | the edit text fields in Account Login page should be clickable | the edit text fields in Account Login page is clickable | pass
DCW_HP_48 | check whether the email address edit text field under Returning Customer option is accepting alphabets,numbers and special characters | 1.click on email address text field 2.enter email id | agfrtyhjuk123@gmail.com | email address edit text field under Returning Customer option should accepting alphabets,numbers and special characters | email address edit text field under Returning Customer option is accepting alphabets,numbers and special characters | pass
DCW_HP_49 | check whether the password edit text field under Returning Customer option is accepting alphabets,numbers and special characters | 1.click on password text field 2.enter password | 345dfrt@bec87 | the password edit text field under Returning Customer option should accepting alphabets,numbers and special characters | the password edit text field under Returning Customer option is accepting alphabets,numbers and special characters | pass
DCW_HP_50 | ensure forgot password option is present or not | 1.locate forgot password |  | forgot password option should be present | forgot password option is present | pass
DCW_HP_51 | check whether navigating to next page when clicking on forgot password | 1.click on forgot password |  | should navigate to next page when clicking on forgot password option | navigating to next page when clicking on forgot password option | pass
DCW_HP_52 | check whether the email address edit text field under forgot password option is accepting alphabets,numbers and special characters | 1.click on email address text field 2.enter email id | amrutharaj2018@gmail.com | email address edit text field under forgot password option should accept alphabets,numbers and special characters | email address edit text field under forgot password option is accepting alphabets,numbers and special characters | pass
DCW_HP_53 | ensure that continue option is present or not | 1.locate continue option |  | continue option should be present | continue option is present | pass
DCW_HP_54 | ensure that back option is present or not | 1.locate back option |  | back option should be present | back option is present | pass
DCW_HP_55 | check whether the recovery mail is send to the entered email id | 1.check the email id |  | email should be send to the entered email id | recovery mail is send to the entered email id | pass
DCW_HP_56 | check whether the error message is showing when the entered emai id and password is incorrect | 1.enter the email id and password 2.click on the login option | avgftth@gmail.com 345dfrt@bec87 | error message should show when the entered emai id and password is incorrect | error message is showing when the entered emai id and password is incorrect | pass
DCW_HP_57 | check whether clicking on Continue option is navigating to Registration page | 1.click on the continue option |  | clicking on Continue option should navigate to Registration page | clicking on Continue option is navigating to Registration page | pass
DCW_HP_58 | check whether all the edit text field are visible or not | 1.check all the edit text field |  | all the edit text field should be visible | all the edit text field are visible | pass
DCW_HP_59 | check whether all the edit text field are clickable or not | 1.click on all the edit text field |  | all the edit text field should be clickable | all the edit text field are clickable | pass
DCW_HP_60 | check whether all the edit text field are editable or not | 1.click on all the edit text field 2.enter details | amrutha raj abgfghjnn23@gmail.com 8976543245 dsefr2345@sdf dsefr2345@sdf | all the edit text field should be editable | all the edit text field is editable | pass
DCW_HP_61 | check whether the first name edit text field is accepting alphabets | 1.click on the first name edit text field 2.enter firstname | amrutha | the first name edit text field should accepting alphabets | the first name edit text field is accepting alphabets | pass
DCW_HP_62 | check whether the last name edit text field is accepting alphabets | 1.click on the last name edit text field 2.enter last name | raj | the last name edit text field should accepting alphabets | the last name edit text field is accepting alphabets | pass
DCW_HP_63 | check whether the email id edit text field is accepting alphabets,numbers and special characters | 1.click on the email id edit text field 2.enter email id | abgfghjnn23@gmail.com | email id edit text field should accept alphabets,numbers and special characters | email id edit text field is accepting alphabets,numbers and special characters | pass
DCW_HP_64 | check whether the telephone edit text field is accepting numbers | 1.click on the telephone edit text field 2.enter telephone number | 8976543245 | the telephone edit text field should accept numbers | the telephone edit text field is accepting numbers | pass
DCW_HP_65 | check whether the password edit text field is accepting numbers ,alphabets,special characters | 1.click on the password edit text field 2.enter password | dsefr2345@sdf | the password edit text field should accept numbers ,alphabets,special characters | the password edit text field is accepting numbers ,alphabets,special characters | pass
DCW_HP_66 | check whether the password confirm edit text field is accepting numbers ,alphabets,special characters | 1.click on the password confirm edit text field 2.enter password | dsefr2345@sdf | the password confirm edit text field should accept numbers ,alphabets,special characters | the password confirm edit text field is accepting numbers ,alphabets,special characters | pass
DCW_HP_67 | check whether the error message is showing when the password entered are incorrect | 1.click on the password confirm edit text field 2.enter password | dsefr2345@sdf77 | error message should show when the password entered are incorrect | the error message is showing when the password entered are incorrect | pass
DCW_HP_68 | check whether the radio button for subscribe option is working or not | 1.locate radio button 2.click on radio button |  | the radio button for subscribe option should work | the radio button for subscribe option is working | pass
DCW_HP_69 | check whether the privacy policy check box is present or not | 1.locate privacy policy check box |  | privacy policy check box should present | privacy policy check box is present | pass
DCW_HP_70 | check whether the error message is showing when any of the field left blank | 1.left any field blank |  | error message should show when any of the field left blank | error message is showing when any of the field left blank | pass
DCW_HP_71 | check whether the success message is showing when clicking on continue | 1.locate continue 2.click on continue |  | success message should show when clicking on continue | success message is showing when clicking on continue | pass

## Sheet3
Module | Defect distribution
Home Page | 13
Our Menu Card | 4
Categories | 1
Contact Us | 1
Gallery | 1
About Us | 1
Add to Cart | 1
Map | 1
Login | 0

## Sheet4
Module Name | Test case failed | Test case passed | Total Test case
Home Page | 13 | 8 | 21
Our Menu Card | 4 | 3 | 7
Categories | 1 | 2 | 3
Contact us | 1 | 1 | 2
Gallery | 1 | 2 | 3
About Us | 1 | 1 | 2
Add to cart | 1 | 0 | 1
Map | 1 | 7 | 8
Login | 0 | 24 | 24